## Sprint1
Issue # | US / Issue Title | Task # | Associated tasks/ Task Description | Due Date | Priority | Risk | Assignee
US.01 | Student: Browse & Search Events using Filters | 1.1 | Frontend: Design UI of Event Browser |  | High
|  | 1.2 | Backend: Events API |  | High
|  | 1.3 | Backend: Search logic |  | Medium
|  | 1.4 | Tests & Documentation |  | Low
US.02 | Student: Save events to calendar | 2.1 | Backend: Save/unsave events API |  | High
|  | 2.2 | Backend: Fetch saved events API |  | High
|  | 2.3 | Frontend: Save button |  | Medium
|  | 2.4 | Frontend: "My Events" Page |  | Medium
|  | 2.5 | Tests & Documentation |  | Low
US.03 | Student: Claim tickets | 3.1 | Backend: Ticket claim API |  | High
|  | 3.2 | Backend: Ticket claim API |  | High
|  | 3.3 | Frontend: Claim ticket button |  | High
|  | 3.4 | Frontend: Ticket confirmation page |  | Medium
|  | 3.5 | Tests & Documentation |  | Low
US.04 | Student: Receive digital ticket with QR code | 4.1 | Backend: Generate Ticket QR code |  | High
|  | 4.2 | Frontend: Add generated ticket to Student Tickets view |  | Medium
|  | 4.3 | Backend: Ticket retrieval API |  | High
|  | 4.4 | Frontend: Ticket validation indicator |  | Medium
|  | 4.5 | Test & Documentation |  | Low
US.05 | Organizer: Create and publish events | 5.1 | Backend: Event creation API | 2025-10-02 | High |  | Renato
|  | 5.2 | Backend: Event publish/unpublish | 2025-10-02 | High |  | Renato
|  | 5.3 | Frontend: Event creation form | 2025-10-02 | High |  | Renato
|  | 5.4 | Frontend: "My Events" Page | 2025-10-02 | Medium |  | Renato
|  | 5.5 | Tests & Documentation | 2025-10-02 | Low |  | Renato
US.06 | Organizer: View event analytics | 6.1 | Backend: Analytics endpoint |  | High
|  | 6.2 | Backend: Data updates |  | Medium
|  | 6.3 | Frontend: Organizer dashboard UI |  | Medium
|  | 6.4 | Tests & Documentation |  | Low
US.07 | Organizer: Manage attendance | 7.1 | Backend: Attendee list export |  | Medium
|  | 7.2 | Backend: QR code validation API |  | High
|  | 7.3 | Frontend: Attendee management page |  | Medium
|  | 7.4 | Frontend: QR validation interface |  | Medium
|  | 7.5 | Tests & Documentation |  | Low
US.08 | Administrator: Approve organizer accounts | 8.1 | Backend: Organizer approval API | 2025-10-02 | High |  | Othmane
|  | 8.2 | Frontend: Admin dashboard | 2025-10-02 | High |  | Othmane
|  | 8.3 | Tests & Documentation | 2025-10-02 | Low |  | Othmane
US.09 | Administrator: Moderate event listings | 9.1 | Backend: Event moderation API | 2025-10-02 | High |  | Alek
|  | 9.2 | Frontend: Event moderation dashboard | 2025-10-02 | High |  | Alek
|  | 9.3 | Logging | 2025-10-02 | Low |  | Alek
|  | 9.4 | Tests & Documentation | 2025-10-02 | Low |  | Alek
US.10 | Administrator: View platform analytics | 10.1 | Backend: Global analytics endpoints | 2025-10-02 | High |  | Alek
|  | 10.2 | Backend: Data aggregation logic | 2025-10-02 | High |  | Alek
|  | 10.3 | Frontend: Analytics dashboard UI | 2025-10-02 | Medium |  | Alek
|  | 10.4 | Tests & Documentation | 2025-10-02 | Low |  | Alek
US.11 | Administrator: Manage organizations & roles | 11.1 | Backend: Organization management API | 2025-10-02 | Medium |  | Klisea
|  | 11.2 | Backend: Role assignment API | 2025-10-02 | High |  | Klisea
|  | 11.3 | Frontend: Admin role+organization management dashboard | 2025-10-02 | Medium |  | Klisea
|  | 11.4 | Tests & Documentation | 2025-10-02 | Low |  | Klisea
US.12 | Global: User Login | 12.1 | Frontend: User login |  | High
|  | 12.2 | Backend: Authorization API |  | High
|  | 12.3 | Backend: Student view API |  | Medium
|  | 12.4 | Tests & Documentation |  | Low

## Sprint2
Issue # | US / Task Title | (US)/ task | Due Date | Associated tasks/ Task Description | Priority | Risk | Responsible
US.03 | Students being able to add themselves to their courses | As a student, I want to be able to add myself to the courses that I am registered to | 2024-09-29 | - create a page for courses that a student is enrolled in - create express route to access a student's courses - create express route to enroll student in course - create modal on course view page with form to add course | High |  | All members of the team
US.04 | Being able to create a course and view course participants as a teacher | As a teacher, I want to be able to create a new course, I want to be able to see which courses I own, and to see which students have joined each course | 2024-09-29 | - create a home page that displays a teacher's courses once logged in - create a button to open course creation page on the teacher home page - create a course creation page where course details can be specified - create a page for each owned course where all the participants can be viewed - create express route to create a new course for a teacher - create express route to return all courses of a teacher - create express toute to return all participant info for a course - Teachers being able to assign students to peer review each other | High |  | I'll sketch a quite design on Figma
US.05 | Students being able to review each other | As a student I wish to be able to give feedback to a teammate I selected and to receive a confirmation message once I submit a review for my teammate(s) | 2024-09-29 | - display list of teammates -rating button - alert message (confirmation) | High
Task.11 | Create a page for courses that a student is enrolled in | US.03 |  | When a student is logged in, they should be redirect to a page where all the courses they are enrolled in are shown. They should have a menu for enroll into a class using a class code | Low |  | kerry
Task.12 | Create an express route to access a student's courses | US.03 |  | Create an api route for returning a list of courses when a student id is supplied | Low |  | kerry
Task.13 | Create express route to enroll student in course | US.03 |  | Create an api route that updates the db by enrolling the student into the given class number | Low |  | marian
Task.14 | Create modal on course view page with form to add course | US.03 |  | Create a modal that gives the option to the user to add a course, sending a request to the api to update the student's enrollment courses | Low |  | marian
Task.15 | Create a home page that displays a teacher's courses once logged in | US.04 |  | Create a page for teachers, once logged in, that displays a grid of courses that were previously created by the teacher. each courses links to a separate page that will display the course code and all the registered participants in the class | Low |  | Jeslyn
Task.16 | Create a button to open course creation page on the teacher home page | US.04 |  | Create a button that opens the page creation window for the teacher | Low |  | Srab
Task.17 | Create a course creation page where course details can be specified | US.04 |  | Create a page for course creation where the teacher can enter the following details: - course title - course code - maximum participants - semester offered | Low |  | Srab
Task.18 | Create a page for each owned course where all the participants can be viewed | US.04 |  | Create a page for each course owned by the teacher that displays the course information and all the registered participants | Low |  | Vin
Task.19 | Create express route to create a new course for a teacher | US.04 |  |  | Low |  | Srab
Task.20 | Create express route to return all courses of a teacher | US.04 |  |  | Low |  | Jeslyn
Task.21 | Create express toute to return all participant info for a course | US.04 |  |  | Low |  | Vin
Task.22 | Teachers being able to assign students to peer review each other (making teams) | US.04 |  |  | Low
Task.23 | Display list of teammates | US.05 |  |  | Low
Task.24 | Rating button | US.05 |  |  | Low
Task.25 | Alert message (confirmation) | US.05 |  |  | Low
Task.26 | Create acceptance test for User Story 1 |  |  |  | Low |  | Sasha
Task.27 | Create acceptance test for User Story 2 |  |  |  | Low |  | Sasha
- | Fix DB & Form | - |  |  | High |  | Vin
- | Setup CI/CD pipeline |  |  |  | High |  | Vin, Marian

## Sprint3
| US / Task Title | (US)/ task | Due Date | Associated tasks/ Task Description | Priority | Risk | Responsible
US.03 |  |  |  |  | High |  | All members of the team
Task.22 | Teachers being able to assign students to peer review each other (making groups) | US.04 | teacher just create a new empty group and assign students to that group |  | High |  | Sasha
Task.23 | Display list of teammates | US.05 | when student clicks on class with group assigned, they see only their group |  | High |  | Kerry
Task.24 | Rating | US.05 | create a rating modal, students should grade on 5-point scale for each of these criteria: Cooperation dimension, Conceptual Contribution, Practical Contribution, and Work Ethic. there's a comment box for each of those criteria add confirmation button |  | High |  | Vin
Task.29 | Create an interface for seeing team visible to teachers | US.05 | when teacher opens course, they see the created groups with: Students in group |  | High |  | Srab
Task.27 | Create an interface for students to select other teammate to rate within their group |  | when student clicks on group, they can see who they can rate and when they click on that person, they can rate them |  | High |  | Jes
Task.28 | Create a dashboard for teacher to view the results of ratings | US.04 | - Create a page that displays a simple and detailed view of the review results for each students - Summary & Detailed look at sprint 3 doc |  | High |  | Marian
Task.29 | Convert acceptance tests from Sprints 1 and 2 to CI/CD |  |  |  | High |  | Vin
Task.30 | Write acceptance for all features of Sprint 3 and integrate them into CI/CD pipeline |  |  |  | High |  | Vin

## Copy of Sprint3
US / Task Title | (US)/ task | Due Date | Associated tasks/ Task Description | Priority | Risk | Responsible
|  |  |  | High |  | All members of the team