## Sprint
Issue # | US / Issue Title | Task # | Associated tasks/ Task Description | Approximate Task Time | Due Date | Story Points | Priority | Risk | Assignee
US.01 | Student: Browse & Search Events using Filters | 1.1 | Frontend: Design UI of Event Browser |  |  |  | High
|  | 1.2 | Backend: Events API |  |  |  | High
|  | 1.3 | Backend: Search logic |  |  |  | Medium
|  | 1.4 | Tests & Documentation |  |  |  | Low
US.02 | Student: Save events to calendar | 2.1 | Backend: Save/unsave events API |  |  |  | High
|  | 2.2 | Backend: Fetch saved events API |  |  |  | High
|  | 2.3 | Frontend: Save button |  |  |  | Medium
|  | 2.4 | Frontend: "My Events" Page |  |  |  | Medium
|  | 2.5 | Tests & Documentation |  |  |  | Low
US.03 | Student: Claim tickets | 3.1 | Backend: Ticket claim API |  |  |  | High
|  | 3.2 | Backend: Ticket claim API |  |  |  | High
|  | 3.3 | Frontend: Claim ticket button |  |  |  | High
|  | 3.4 | Frontend: Ticket confirmation page |  |  |  | Medium
|  | 3.5 | Tests & Documentation |  |  |  | Low
US.04 | Student: Receive digital ticket with QR code | 4.1 | Backend: Generate Ticket QR code |  |  |  | High
|  | 4.2 | Frontend: Add generated ticket to Student Tickets view |  |  |  | Medium
|  | 4.3 | Backend: Ticket retrieval API |  |  |  | High
|  | 4.4 | Frontend: Ticket validation indicator |  |  |  | Medium
|  | 4.5 | Test & Documentation |  |  |  | Low
US.05 | Organizer: Create and publish events | 5.1 | Backend: Event creation API |  | 2025-10-02 |  | High |  | Renato
|  | 5.2 | Backend: Event publish/unpublish |  | 2025-10-02 |  | High |  | Renato
|  | 5.3 | Frontend: Event creation form |  | 2025-10-02 |  | High |  | Renato
|  | 5.4 | Frontend: "My Events" Page |  | 2025-10-02 |  | Medium |  | Renato
|  | 5.5 | Tests & Documentation |  | 2025-10-02 |  | Low |  | Renato
US.06 | Organizer: View event analytics | 6.1 | Backend: Analytics endpoint |  |  |  | High
|  | 6.2 | Backend: Data updates |  |  |  | Medium
|  | 6.3 | Frontend: Organizer dashboard UI |  |  |  | Medium
|  | 6.4 | Tests & Documentation |  |  |  | Low
US.07 | Organizer: Manage attendance | 7.1 | Backend: Attendee list export |  |  |  | Medium
|  | 7.2 | Backend: QR code validation API |  |  |  | High
|  | 7.3 | Frontend: Attendee management page |  |  |  | Medium
|  | 7.4 | Frontend: QR validation interface |  |  |  | Medium
|  | 7.5 | Tests & Documentation |  |  |  | Low
US.08 | Administrator: Approve organizer accounts | 8.1 | Backend: Organizer approval API |  | 2025-10-02 |  | High |  | Othmane
|  | 8.2 | Frontend: Admin dashboard |  | 2025-10-02 |  | High |  | Othmane
|  | 8.3 | Tests & Documentation |  | 2025-10-02 |  | Low |  | Othmane
US.09 | Administrator: Moderate event listings | 9.1 | Backend: Event moderation API |  | 2025-10-02 |  | High |  | Alek
|  | 9.2 | Frontend: Event moderation dashboard |  | 2025-10-02 |  | High |  | Alek
|  | 9.3 | Logging |  | 2025-10-02 |  | Low |  | Alek
|  | 9.4 | Tests & Documentation |  | 2025-10-02 |  | Low |  | Alek
US.10 | Administrator: View platform analytics | 10.1 | Backend: Global analytics endpoints |  | 2025-10-02 |  | High |  | Alek
|  | 10.2 | Backend: Data aggregation logic |  | 2025-10-02 |  | High |  | Alek
|  | 10.3 | Frontend: Analytics dashboard UI |  | 2025-10-02 |  | Medium |  | Alek
|  | 10.4 | Tests & Documentation |  | 2025-10-02 |  | Low |  | Alek
US.11 | Administrator: Manage organizations & roles | 11.1 | Backend: Organization management API |  | 2025-10-02 |  | Medium |  | Klisea
|  | 11.2 | Backend: Role assignment API |  | 2025-10-02 |  | High |  | Klisea
|  | 11.3 | Frontend: Admin role+organization management dashboard |  | 2025-10-02 |  | Medium |  | Klisea
|  | 11.4 | Tests & Documentation |  | 2025-10-02 |  | Low |  | Klisea
US.12 | Global: User Login | 12.1 | Frontend: User login |  |  |  | High
|  | 12.2 | Backend: Authorization API |  |  |  | High
|  | 12.3 | Backend: Student view API |  |  |  | Medium
|  | 12.4 | Tests & Documentation |  |  |  | Low